## README
Last Update | 2018-10-19
Author | Split Splat – Elijah Cain, Arman Irani, Aaron Ha, Mitch Kim, Saul Plateros
Email | ecain001@ucr.edu, aiaran002@ucr.edu, aha011@ucr.edu, splat002@ucr.edu
Description | [Split Splat] Developing an application to handle splitting bills among a group of friends
Tabs | Notes
"Product Backlog" | Should be initialized with the user stories and their estimated efforts (i.e., story points)
Depending on the amount of story points, some stories may need to be split into smaller stories
Add "Acceptance Criteria" to each user story by "insert note" to a spreadsheet cell (right click the cell)
"Acceptance Criteria" define what it means by "Done"
"Task Board" | "To Do" is initialized with tasks defined during the Sprint Planning Meeting (i.e., sprint backlog)
Tasks are expected to have similar sizes, each with a time cost of roughly 3-4 hours
Add "Details" and "Acceptance Criteria" to a task by "insert note" to a spreadsheet cell (right click the cell)
Minimize task assignments at the Sprint Planning Meeting
During a sprint, members who become available can pull tasks from the "To Do" list by moving them to "In Progress" and attaching his/her name
Inform your teammates know before you pull a task from "To Do" list
"To Verify" should be pulled by a different team member; This is a good time to perform code review and unit testing
A task in "Done" list should have its verifier's name appended
"Archives" | At the end of a Sprint, finished tasks are moved to "Archives"; Unfinished tasks are moved to the next Sprint Planning Meeting
"Burndown Chart" | At the end of a Sprint, update the "Burndown Chart"
if "Story Points (Remaining)" is above the "Ideal", it would be an indicator for slow progress

## Product Backlog
ID | Story Name | Story (small features) | Story Points | Priority | Comments
1 | User Account | As a user, I want to be able to either sign in with my email or Google account. Also, I want to be able to delete my account | 3 | 1
2 | To-do List | As a user, I want to be able to keep track of and organize tasks | 2 | 2
3 | Mobile App | As a user in a group of people, I want to be able to split a bill among the group using a mobile app | 4 | 3
| Total |  | 9
Note on C2: Acceptance Criteria: 1. Establish a log-in page 2. Successfully sign-in with e-mail 3. Forgot password? 4. Successfully delete an account
Note on C3: Acceptance Criteria: 1. Display a list of tasks 2. Able to create tasks 3. Edit tasks
Note on C4: Acceptance Critera: 1. Mobile app successfully launches 2. Capable of signing in with account 3. Establish a group of users 4. Split a bill among the group

## Task Board
To Do (Sprint Backlog) | In Progress | Testing | Done
Task 1: User Account (Saul Plateros & Arman Irani)
Task 2: To-do List (Saul Plateros)
Task 3: Mobile App (Saul Plateros)
Task 5: ...
Task 6: ...
Task 7: ...
Task 8: ...
...
Team | Group Members
Front-end Team | Aaron Ha, Mitch Kim, Saul Plateros
Back-end Team | Elijah Cain, Arman Irani

## Archives
Sprint ID | Scrum Master | Tasks Completed
1 | Elijah Cain | Task 1: User Account (Saul Plateros & Arman Irani)
2 | Elijah Cain | Task 2: To-do List (Saul Plateros)
3

## Burndown Chart
Sprint ID | Story Points (Total) | Story Points (Completed) | Story Points (Accumulated) | Story Points (Remaining) | Ideal
0 | 9 | 0 | 0 | 9 | 9
1 | 9 | 3 | 3 | 6 | 6
2 | 9 | 2 | 5 | 4 | 3
3 | 9 | 2 | 7 | 2 | 0
4 |  |  |  |  | -3
5 |  |  |  |  | -6
6 |  |  |  |  | -9
7 |  |  |  |  | -12
8 |  |  |  |  | 0