## README
Last Update | 2018-10-30
Author | Split Splat – Elijah Cain, Arman Irani, Aaron Ha, Mitch Kim, Saul Plateros
Email | ecain001@ucr.edu, aiaran002@ucr.edu, aha011@ucr.edu, splat002@ucr.edu
Description | [Split Splat] Developing an application to handle splitting bills among a group of friends
Tabs | Notes
"Product Backlog" | Should be initialized with the user stories and their estimated efforts (i.e., story points)
Depending on the amount of story points, some stories may need to be split into smaller stories
Add "Acceptance Criteria" to each user story by "insert note" to a spreadsheet cell (right click the cell)
"Acceptance Criteria" define what it means by "Done"
"Task Board" | "To Do" is initialized with tasks defined during the Sprint Planning Meeting (i.e., sprint backlog)
Tasks are expected to have similar sizes, each with a time cost of roughly 3-4 hours
Add "Details" and "Acceptance Criteria" to a task by "insert note" to a spreadsheet cell (right click the cell)
Minimize task assignments at the Sprint Planning Meeting
During a sprint, members who become available can pull tasks from the "To Do" list by moving them to "In Progress" and attaching his/her name
Inform your teammates know before you pull a task from "To Do" list
"To Verify" should be pulled by a different team member; This is a good time to perform code review and unit testing
A task in "Done" list should have its verifier's name appended
"Archives" | At the end of a Sprint, finished tasks are moved to "Archives"; Unfinished tasks are moved to the next Sprint Planning Meeting
"Burndown Chart" | At the end of a Sprint, update the "Burndown Chart"
if "Story Points (Remaining)" is above the "Ideal", it would be an indicator for slow progress

## Product Backlog
ID | Story Name | Story (small features) | Story Points | Priority | Comments
1 | Contact List | As a user of the app, I want to be able to add people through email or phone number | 4 | 1
2 | Split Algorithm | Develop a calculation algorithm that will resolve any balances | 3 | 2
3 | Mobile App | As a user in a group of people, I want to be able to split a bill among the group using a mobile app | 4 | 3
4 | E-mail Notifications | As a user of the app, I want to receive e-mail notifications for any updates within my groups | 1 | 4
| Total |  | 12
Note on C2: Acceptance Criteria: 1. Successfully add user by e-mail 2. Successfully add user by phone number 3. Displays a list of contacts
Note on C3: Acceptance Criteria: 1. Succesfully split the bill among a group 2. Only users within a group sees the same shared data
Note on C4: Acceptance Critera: 1. Mobile app successfully launches 2. Capable of signing in with account 3. Establish a group of users 4. Split a bill among the group
Note on C5: Acceptance Criteria: 1. Users successfully receive e-mails if payments or bills pertain to the user

## Task Board
To Do (Sprint Backlog) | In Progress | Testing | Done
Task 1: Contact List (Front-end Team & Back-end Team)
Task 2: Split Algorithm (Front-end Team & Back-end Team)
Task 3: Mobile App (Saul Plateros)
Task 4: E-mail Notifications
Task 5: …
Task 6: ...
Task 7: ...
Task 8: ...
...
Team | Group Members
Front-end Team | Aaron Ha, Mitch Kim, Saul Plateros
Back-end Team | Elijah Cain, Arman Irani

## Archives
Sprint ID | Scrum Master | Tasks Completed
1 | Elijah Cain
2
3

## Burndown Chart
Sprint ID | Story Points (Total) | Story Points (Completed) | Story Points (Accumulated) | Story Points (Remaining) | Ideal
0 | 12 | 0 | 0 | 12 | 12
1 | 12 | 0 | 0 | 12 | 9
2 | 12 | 0 | 0 | 12 | 6
3 | 12 | 0 | 0 | 12 | 3
4 | 12 | 0 | 0 | 12 | 0
5 |  |  |  |  | -6
6 |  |  |  |  | -9
7 |  |  |  |  | -12
8 |  |  |  |  | 0